## Manual Chart
Advanced Software Engineering
Team members: Shayne, Calum, Alex, Jack, AJ
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Litrature Review | Initial Planning |  |  | 4 | ALL
Introduction of team members
Initial project ideas
Draft UML
Litrature Review | Iteration 1 (basic implementation, just drinks) & UML submission |  |  | 5 | ALL
Project Integration | Iteration 2 - Add in food items |  |  | 5 | All
| Iteration 3 - Add in "other" items and discounts |  |  | 3 | All
| Iteration 4 - Add in "extras", ie bacon, extra shot…etc |  |  | 2 | All
| Final adjustments |  |  | 4 | All